## Sheet1
SendGrid Integration Estimate (Draft)
If no module available
| min | max | most likely
Add custom module
Setup and registration to the service | 1 | 1 | 1
Install libraries (php) | 1 | 2 | 2
Integrate library to drupal (custom module) | 2 | 3 | 3
Refactor alert class | 2 | 3 | 3
Add email service | 1 | 2 | 2
Refactor and adjust other modules | 2 | 3 | 3
Examine the behavior of email (bulk email) | 2 | 3 | 3
Testing (tester)
Total | 10 | 16 | 16
If a module is available
Setup and registration to the service | 1 | 1 | 1
Intallation and configuration | 1 | 2 | 2
Refactor Alert class | 2 | 3 | 3
Examine behavior of emails (bulk email) | 2 | 3 | 3
Testing (tester)
Total | 6 | 9 | 9